🔥  CANNAGRUDGE

OFFICIAL MARKETING PLAN  ·  APRIL 25, 2026

Dunn's Arena  ·  Litchfield Park, AZ  ·  21+

THE SITUATION

April 25, 2026 — 46 days out. Here's what we're working with:

3,000-person capacity event at Dunn's Arena, Litchfield Park, AZ — this is a major venue

Own ticketing platform on cannagrudge.com — no third-party cut

Large warm email database ready to deploy immediately

Daily dispensary presence across the Phoenix metro market

Nirvana partnership — 10 locations across the West Valley

13 recognized AZ cannabis brands competing — each with their own audience

Dual audience: cannabis consumers + Phoenix combat sports fans

PAID ADVERTISING BUDGET

Total recommended spend: ~$7,500–$9,000. At 3,000 capacity you need volume — not just warm email opens. This budget reflects a real push across every available channel. Concentrate 40% of Traffic Roots and Facebook budget in the final 14 days when purchase intent peaks.

| Channel | Budget | What It Buys |
| --- | --- | --- |
| Traffic Roots — Retargeting | $600 | Serve ads to email list + site visitors who didn't convert. Highest ROI — warm audience already exposed. |
| Traffic Roots — Prospecting | $1,200 | Cold geo-targeted display/mobile ads, Phoenix metro 21+ cannabis + nightlife audiences at scale |
| Traffic Roots — Video Pre-Roll | $800 | 15-second video pre-roll on cannabis publisher sites — highest recall format, critical for a 3k event |
| Facebook / Instagram Ads | $1,500 | Frame as entertainment event. Target 21–45, Phoenix metro + surrounding cities, combat sports + nightlife. Retarget all site visitors. |
| Google Display / Search | $800 | "Cannabis event Phoenix," "fight night AZ," "things to do Phoenix April 2026" — high buyer intent searches |
| Reddit Promoted Posts | $300 | r/AZTrees, r/phoenix, r/arizona — promoted posts look native, no cannabis ad policy issues |
| TikTok Ads | $500 | Spark Ads from brand partner posts that perform organically — amplify what's already working |
| Influencer / Creator Outreach | $500 | 2–4 AZ cannabis/nightlife creators posting about the event to their audiences. Negotiate tickets + cash. |
| Flier Printing | $400 | 5,000 fliers with QR codes + promo codes for full dispensary market coverage |
| Digital Screen Assets | $150 | Formatted slides for in-store digital screens across dispensary network |
| Budtender Incentive Prize Pool | $300 | VIP tickets + product + cash — top referring locations compete hard when the stakes are real |
| TOTAL | ~$7,050–$8,550 | Full multi-channel push scaled for 3,000 seats |

PHASE 1 — IGNITION  (March 10–20)

Email Blast #1 — "The Announcement"

Send this week. The database is warm — use it now.

Subject Line (A/B test two):

🔥 AZ's biggest cannabis event is 46 days away

The brands you smoke every day are about to fight

Email Strategy:

Hero image — best event flier or graphic, full width

One punchy paragraph: what it is, where, when — no walls of text

List ALL 13 competing brand names — customers recognize them, instant credibility

Highlight the experience: live boxing, JumboTron, free tattoos, vendor expo, music

One CTA button: "Get Tickets → cannagrudge.com" — nothing else

If it doesn't fit on a phone screen above the fold, it's too long

Exclusive promo code:

EARLYBIRD15 — 15% off, expires March 24. Email list only. Makes them feel VIP.

Send Specs:

Tuesday or Wednesday, 10–11am AZ time

Segment: cannabis-adjacent contacts first, then full blast

Track open rate and CTR — this data tells you how warm the list actually is

Google Business Profile — Event Listing

Do this today. Free. Highest-intent local traffic you can get.

Create or claim the CannaGrudge Google Business Profile

Add the April 25 event — shows up in Google Search and Maps for West Valley searches

Keywords: "cannabis event Phoenix," "fight night Litchfield Park," "AZ brand battle"

Add event image, direct ticket link, full description

This is organic search placement you cannot buy at any reasonable price

Facebook Event — Create & Seed

Create an official Facebook Event for April 25 from the CannaGrudge page

Personal invites to every contact — personal invites convert higher than mass invites

Ask each competing brand to co-host or share the event from their page

Share immediately in these groups:

Arizona Cannabis Community

AZ Stoners / Phoenix 420 groups

West Valley Phoenix events groups

Arizona Fight Fans / Combat Sports AZ groups — this is a boxing event too

💡 KEY INSIGHT: You have a dual audience — cannabis consumers AND boxing/MMA fans in AZ. Most marketing only targets one. A "celebrity boxing + cannabis" angle hits both — tap the fight fan community actively.

Reddit — r/AZTrees (50k+ Members)

Post: "CannaGrudge is April 25 — 13 AZ brands boxing for bragging rights at Dunn's Arena"

Include all brand names — fans of those brands will upvote and share

Reply to every comment in the first 2 hours (Reddit algorithm rewards early engagement)

$20–$50 Reddit promoted post targeting r/AZTrees + r/phoenix for extra reach

Post countdown updates at 2-week and 1-week marks

PHASE 2 — BUILD THE FIRE  (March 20 – April 7)

Email Blast #2 — "Meet the Brands"  (Send ~March 20–22)

Subject:

The lineup is set. 13 brands. One winner. 🥊

Show all 13 brand logos — frame it like a fight card: "In the ring on April 25..."

One-liner on each brand — make their fans feel represented

Restate the full event experience

Show ticket tiers and pricing clearly

Remind about EARLYBIRD15 code with deadline pressure if still active

💡 Each brand has customers who will forward this email. You're leveraging 13 brands' audiences in a single send — no cost.

Brand Partner Content — Activate Their Audiences

This is your biggest free marketing lever. Every competing brand has followers who are your exact target demo.

What to give each brand:

A co-branded graphic — their logo + CannaGrudge + April 25 date

2–3 pre-written caption options for Instagram and Facebook (make it easy for them)

The direct ticket link

Ask for minimum one post per week between now and the event

How to frame it to them:

"Their fans vote with ticket purchases. If your brand gets the biggest turnout, you own those bragging rights. Push hard." — Give them a reason to care.

Traffic Roots — Launch Paid Display Campaign

Platform: trafficroots.com — the only fully cannabis-legal programmatic ad network

Geo-target:

Phoenix metro + specifically West Valley: Peoria, Glendale, Goodyear, Avondale, Buckeye, Litchfield Park

Audience:

21+, cannabis interest, nightlife + event attendees

Formats:

Static banner (300x250, 728x90) + mobile interstitial + video pre-roll

Retargeting:

Upload email list as custom audience — serve ads to openers who didn't convert. Highest-efficiency spend.

Creative:

Bold event graphic, date and venue visible at a glance, single GET TICKETS CTA

Instagram / TikTok Content Calendar

| Day | Content Type | What to Post |
| --- | --- | --- |
| Monday | Brand Spotlight | One competing brand — hype their entry, tag them |
| Wednesday | Behind the Scenes | Venue, prep, merch, team activity |
| Thursday | Countdown | "30 days / 14 days until CannaGrudge" graphic |
| Friday | Ticket Push | "Weekend plans? April 25 →" with ticket link |
| Daily Story | Engagement | Countdown sticker, polls ("Who wins — Nirvana or Tyson?"), ticket link |

🎯 TikTok angle: "13 cannabis brands are about to settle who's #1 in AZ." Get brand reps to film 10-second trash-talk clips at each other. Pure engagement bait — this format can go viral in the cannabis content space.

Email Blast #3 — "The Experience"  (Send ~April 1)

Subject:

Free tattoos. Live fights. Open bar vendors. April 25.

Shift the message from "what is it" to "what will you experience that night."

Walk them through the night hour by hour — make them feel like they're already there

Free tattoos — if confirmed, this is a massive hook for this demographic

JumboTron watch party, music/DJ, vendor expo — paint the full picture

Ticket tiers clearly explained — what each tier includes, price, availability

Add a sold ticket count or "X tickets remaining" if numbers support FOMO

PHASE 3 — CLOSE THE SEATS  (April 7–22)

Email Blast #4 — "Two Weeks Out"  (Send April 7)

Subject:

2 weeks. 🔥 Last chance for the good seats.

Urgency: ticket count, capacity reminder (3,000-person venue — big enough to feel possible, real enough to sell out)

Show what they're missing — brand content, venue photos, hype material

Introduce "bring a friend" incentive:

PLUS1 promo code — buy 2, second ticket 10% off. Drives group purchases.

Email Blast #5 — "Final 7 Days"  (Send April 18)

Subject:

Saturday. You in or out?

Keep it extremely short. 3 sentences above the fold. Urgency through simplicity.

"3,000 people. One night. Saturday April 25. You in?"

Large ticket button — only CTA on the email

Nothing else. The brevity is the message.

SMS Blast (If You Have Numbers)

📱 SMS open rate is 95%+ vs ~25% for email. If you have numbers, use them.

Text 1 — 7 days out: "CannaGrudge is THIS Saturday at Dunn's Arena. Tickets → [link]"

Text 2 — 24 hours out: "Tomorrow night. See you there 🔥 [link]"

Short, direct, no subject line needed — just the message and link

Free Local Event Listings

Low effort, free reach. Submit to all three today:

Patch.com

Litchfield Park / Goodyear / Peoria editions — free community event submissions

AZCentral.com

Events calendar — free submit, reaches large Phoenix metro audience actively looking for things to do

Do602.com

Phoenix events discovery site — cannabis-adjacent audience already using the platform

DISPENSARY PRESENCE — MAXIMIZING DAILY FLOOR TIME

Your teams are already on the floor every day across a massive footprint. The goal is to stop treating these visits as flier drops and start running them as mini campaign activations. Every single visit should convert floor time into ticket sales.

Location Tier System

| Tier | Locations | Visit Frequency | Activation Level |
| --- | --- | --- | --- |
| Tier 1 — Anchor | Nirvana (all 10 locations) | 2x per week | Full activation — script, screen, POS, budtender briefing |
| Tier 2 — Partner | Mint + other partner accounts | 1x per week | Standard activation — POS placement, budtender touchpoint |
| Tier 3 — Coverage | Broader market dispensary accounts | 1x per 2 weeks | Flier refresh + quick budtender mention |

The Floor Activation Script

Train every team member to deliver this exact message. Consistency is everything:

"Hey — you know the brands on your shelf right here? [hold up flier] They're all boxing each other for bragging rights on April 25 at Dunn's Arena. 3,000 people, live fights, free tattoos, vendor expo — it's 21+. Tickets are $40, there's a promo code on the flier for a discount. It's going to sell out."

Why this script works:

Leads with brands they already recognize and trust — instant relevance

Gives them a physical flier with QR code — something to hold and scan later

Mentions 3,000 people — makes it sound like a real event, not a small local gathering

The tattoo detail is unusual enough to stick in memory

Vendor Day Checklist — Every Tier 1 & Tier 2 Visit

ON ARRIVAL:

Restock fliers at POS — top of the stack, face up, QR code visible

Ask manager or lead budtender: "Can we get the CannaGrudge slide up on the screen this week?"

Drop a small stack in the waiting area

DURING FLOOR TIME:

Personally hand a flier to anyone browsing — do not leave it to them to pick one up

Deliver the activation script to as many customers as possible

Scan your own QR code in front of the customer to show it works and where it goes

BEFORE LEAVING:

Remind the on-duty budtender about the promo code contest — top store wins

Log the visit: location name, fliers left, screen updated Y/N, budtender conversation Y/N

Nirvana Partnership — 10 Locations, Maximum Activation

Nirvana is not just a distribution point — they are a competing brand with loyal customers who are your warmest audience. Use every channel available through them:

Ask Nirvana to blast the event to their customer loyalty database — a "Nirvana presents CannaGrudge" co-branded send

Get the event posted on Nirvana's official social channels — their followers already trust the brand

Push for 18x24 poster or counter display at all 10 locations — elevates beyond a flier

Get a CannaGrudge slide on rotation on all in-store digital screens

🏆 Nirvana angle for in-store: "Come cheer for us April 25" — their customers feel tribal loyalty. Nirvana fans showing up is brand support, not just ticket sales.

Budtender Incentive Contest

You have 15–20+ locations with multiple budtenders each. This is a free sales team — you just need to activate them.

How it works:

Every location gets a unique promo code tied to that store (e.g., NIRVANA75TH, NIRVANAPEORIA, MINTTEMPE)

Codes are already trackable in your promo code dashboard

Top 3 locations by redemptions each win: 2 VIP tickets + branded CannaGrudge package

Announce the contest to every manager today so budtenders know from day one

Send a mid-contest leaderboard update around April 10 — "Location X is in the lead" — drives competition

💰 A $300 prize pool activating 20+ locations can generate 100–200+ ticket sales across your network. Real prizes drive real competition — this is the highest ROI item in the entire plan.

FLIER REQUIREMENTS CHECKLIST

Every flier hitting dispensary floors must have all of the following. A flier without a QR code and promo code is not working hard enough:

Event name + date + venue — readable in under 2 seconds

QR code linking directly to cannagrudge.com/tickets

A promo code for a discount (use DISPENSARY for general floor fliers)

All 13 brand logos — customers recognize them, it's instant social proof

21+ notice — required

cannagrudge.com URL

PROMO CODE STRATEGY

All codes are live in your existing promo code system. Deploy them by channel so you can track exactly which sources are converting:

| Code | Discount | Who Gets It | Expires |
| --- | --- | --- | --- |
| EARLYBIRD15 | 15% off | Email Blast #1 — subscribers only | March 24 |
| DISPENSARY | $5 off | General fliers on all dispensary floors | April 20 |
| NIRVANA[STORE] | $5 off | Store-specific codes for budtender contest | April 20 |
| PLUS1 | 10% off 2+ tickets | Email Blast #4 — bring a friend | April 22 |
| LASTCALL | $3 off | Final email blast + social media | April 24 |

METRICS — WHAT TO TRACK EVERY MONDAY

Your analytics dashboard is already built at cannagrudge.com/analytics. Check these weekly:

Ticket page visits vs. conversions —

If traffic is up but conversions are flat, the page or price is the issue, not the marketing.

Promo code redemptions by code —

Tells you exactly which channel is actually selling tickets. Follow the money.

Email open rates —

Below 20% means subject lines need work. Above 35% means the list is hot — send more.

Traffic sources —

Which referrers are sending buyers. Double down on what's working.

THE ONE THING

🥊 If you only do one thing beyond sending the email blast — get every competing brand to post about CannaGrudge to their own Instagram this week.

13 brands. Each with thousands of followers. Every follower is your exact target demo. They have a personal reason to promote because their brand is competing.

That's earned media you cannot buy at any price.

EVENT TIMELINE SUMMARY

| Week | Dates | Priority Actions |
| --- | --- | --- |
| Week 1 | Mar 10–16 | Email Blast #1 · Google Business listing · Facebook Event · Budtender contest launch · r/AZTrees post |
| Week 2 | Mar 17–23 | Brand partner content activation · Traffic Roots campaign launch · Daily social posting starts |
| Week 3 | Mar 24–30 | Email Blast #2 (brand roster) · Facebook/Instagram ads live · Nirvana loyalty email blast |
| Week 4 | Mar 31–6 | Email Blast #3 (the experience) · Mid-contest leaderboard update · Ramp social posting |
| Week 5 | Apr 7–13 | Email Blast #4 (2 weeks out) · PLUS1 code live · Heavy paid ad spend begins |
| Week 6 | Apr 14–20 | Final dispensary push · Free local listings (Patch, AZCentral, Do602) |
| Week 7 | Apr 21–24 | Email Blast #5 · SMS blast (if available) · LASTCALL code · Full social blitz |
| Event Day | Apr 25 | Behind-the-scenes content · Live posts · Brand arrival coverage · Social throughout the night |

CannaGrudge  ·  April 25, 2026  ·  Dunn's Arena, Litchfield Park AZ  ·  cannagrudge.com